## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Naveen | 2026-02-16 | Unused imports were not being detected correctly for certain Python files | Sprint 1 | Self | Logical | Improved AST traversal logic to correctly identify unused imports | 2026-02-17 | Closed | Issue resolved and validated with sample programs
2 | Naveen | 2026-02-16 | PEP8 style violations were not highlighted consistently in the output | Sprint 1 | Self | Standards | Integrated stricter PEP8 checks and improved formatting rules | 2026-02-17 | Closed | Style detection accuracy improved
3 | Naveen | 2026-02-20 | Getting wrong suggestions and lengthy code which is not relevant for user | Sprint 2 | Self | Maintainability | Finetuned the AI Prompt for getting better and optimized code for user | 2026-03-04 | Closed | Got the optimized code from AI for the given code and explaining the need if correction of code.
4 | Naveen | 2026-03-20 | AI is generating Control Flow Graphs (CFG) which looks messy and complex to user to understand | Sprint 3 | Self | Maintainability | Finetuned the AI Prompt for getting better and optimized Control Flow Graphs (CFG's) for better visualization of code for user | 2026-03-20 | Closed | Got the Optimized Control Flow Graphs (CFG's) from AI for visualization of code for user.
5 | Naveen | 2026-03-21 | Ai is not explaining the code in Ask AI (chatbot) module | Sprint 4 | Self | User Interface | Finetuned and maintained the explainability of code and have teach new concepts to user like a personal trainer | 2026-04-01 | Closed | Finetuned and maintained the explainability of code and AI is teaching new concepts to user like a personal trainer when user prompt for AI about specific topics which are related to coding.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others